Project Planning Phase

Project Planning Template

Product Backlog, Sprint Planning, Stories & Story Points

Date: 15 February 2025
Team ID: __________
Project Name: ServiceNow Incident / Service Request Management System
Maximum Marks: 5 Marks

1. Product Backlog, Sprint Schedule and Estimation

Story Point Scale

| Story Point | Complexity |
| --- | --- |
| 1 | Very Easy Task |
| 2 | Normal Task |
| 3 | Moderate Task |
| 5 | Difficult Task |

Product Backlog

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Form Configuration | USN-1 | As a user, I can access the Incident/Service Request form and enter the required information. | 2 | High | __________ |
| Sprint-1 | Form Configuration | USN-2 | As a user, I can select category, priority, state, and other relevant fields while creating a request. | 2 | High | __________ |
| Sprint-1 | Client Script | USN-3 | As a user, I can receive validation when mandatory information is missing before submitting a request. | 3 | High | __________ |
| Sprint-1 | Client Script | USN-4 | As a user, I can have appropriate field values automatically populated when the form loads. | 2 | Medium | __________ |
| Sprint-2 | Client Script | USN-5 | As a user, I can receive an error message when invalid information is entered. | 3 | High | __________ |
| Sprint-2 | UI Policy | USN-6 | As a user, I can see only the fields relevant to my selected category or request type. | 3 | High | __________ |
| Sprint-2 | UI Policy | USN-7 | As a user, required fields automatically become mandatory based on the selected condition. | 2 | High | __________ |
| Sprint-2 | UI Policy | USN-8 | As a user, confirmed or completed records can have selected fields made read-only. | 3 | Medium | __________ |
| Sprint-3 | Integration | USN-9 | As an administrator, I can integrate Client Scripts and UI Policies with the Incident/Request form. | 5 | High | __________ |
| Sprint-3 | Notification | USN-10 | As a user, I can receive notifications when my request is created, updated, or completed. | 3 | Medium | __________ |
| Sprint-3 | Testing | USN-11 | As an administrator, I can test the complete form workflow and verify Client Script and UI Policy behaviour. | 5 | High | __________ |
| Sprint-3 | Testing | USN-12 | As an administrator, I can identify and fix validation or dynamic-form issues before deployment. | 3 | Medium | __________ |

2. Sprint-wise Story Point Calculation

Sprint-1

Form Configuration + Basic Client Script

- USN-1 = 2

- USN-2 = 2

- USN-3 = 3

- USN-4 = 2

Total Story Points in Sprint-1 = 2 + 2 + 3 + 2 = 9

Sprint-2

Advanced Client Script + UI Policy

- USN-5 = 3

- USN-6 = 3

- USN-7 = 2

- USN-8 = 3

Total Story Points in Sprint-2 = 3 + 3 + 2 + 3 = 11

Sprint-3

Integration + Notification + Testing

- USN-9 = 5

- USN-10 = 3

- USN-11 = 5

- USN-12 = 3

Total Story Points in Sprint-3 = 5 + 3 + 5 + 3 = 16

3. Project Tracker, Velocity & Burndown Chart

Sprint Duration: 6 Days

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 6 Days | 17 Feb 2025 | 22 Feb 2025 | 9 | 22 Feb 2025 |
| Sprint-2 | 11 | 6 Days | 24 Feb 2025 | 01 Mar 2025 | 11 | 01 Mar 2025 |
| Sprint-3 | 16 | 6 Days | 03 Mar 2025 | 08 Mar 2025 | 16 | 08 Mar 2025 |

Total Story Points

Total = 9 + 11 + 16 = 36 Story Points

4. Velocity Calculation

Velocity represents the average number of story points completed by the team per sprint.

Formula:

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points = 36

Number of Sprints = 3

Velocity = 36 / 3

Velocity = 12 Story Points per Sprint

Team Velocity

The team's average velocity is 12 Story Points per Sprint.

5. Average Velocity Per Day

Each sprint has a duration of 6 days.

Formula:

Average Velocity per Day

= Total Story Points / Total Sprint Days

Total Sprint Days = 3 × 6 = 18 days

Average Velocity per Day

= 36 / 18

= 2 Story Points per Day

Therefore, the team completes approximately 2 Story Points per day based on the planned sprint capacity.

6. Burndown Chart Data

The burndown chart represents the amount of work remaining over time.

Total Project Work = 36 Story Points

For a simple ideal burndown over 18 working days:

| Day | Ideal Story Points Remaining |
| --- | --- |
| Day 0 | 36 |
| Day 3 | 30 |
| Day 6 | 24 |
| Day 9 | 18 |
| Day 12 | 12 |
| Day 15 | 6 |
| Day 18 | 0 |

Burndown Interpretation

At the beginning of the project, 36 story points remain. As the team completes Client Scripts, UI Policies, integration, notifications, and testing, the remaining workload decreases. At the end of Sprint-3, the planned work reaches 0 remaining story points.

7. Sprint Goals

Sprint-1 Goal

To configure the ServiceNow Incident/Service Request form and implement basic Client Scripts for form validation and automatic field population.

Sprint-2 Goal

To implement dynamic UI behaviour using UI Policies and complete advanced Client Script validation.

Sprint-3 Goal

To integrate Client Scripts and UI Policies, configure notifications, perform complete testing, and prepare the solution for deployment.

8. Final Project Deliverables

At the completion of the three sprints, the project will provide:

- ServiceNow Incident/Service Request form.

- Client Script for onLoad behaviour.

- Client Script for onChange validation.

- Client Script for onSubmit validation.

- UI Policy for mandatory fields.

- UI Policy for field visibility.

- UI Policy for read-only fields.

- Dynamic form behaviour based on conditions.

- Request/incident notifications.

- End-to-end testing and validation.